## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a developer, I want a secure coding and code-quality knowledge base built from standard sources (OWASP Top 10:2025, OWASP Cheat Sheets, PEP 8, Google Python/Java style guides) so that the agents can give standards-based guidance. | MUST HAVE | none | Bishalakshi | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a developer, I want to upload a .py / .java file or paste code on the same screen. | MUST HAVE | none | Bishalakshi | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a developer, I want the language (Python or Java) to be detected automatically, without a dropdown. | MUST HAVE | US-02 | Bishalakshi | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a developer, I want syntax errors to be highlighted on the exact line in the code view. | MUST HAVE | US-03 | Bishalakshi | 3- Completed
Sprint 1 | Sprint 1 | US-05 | As a developer, I want Submit to be enabled only when the code has no syntax errors. | SHOULD HAVE | US-04 | Bishalakshi | 3- Completed
Sprint 1 | Sprint 1 | US-06 | As a developer, I want the risky patterns in my code (SQL built from strings, hardcoded secrets, weak hashes, unsafe deserialization) matched with OWASP and code-quality guidance retrieved from the knowledge base. | MUST HAVE | US-01, US-05 | Bishalakshi | 3- Completed
Sprint 1 | Sprint 1 | US-07 | As a reviewer, I want the system architecture, agent responsibilities, orchestration flow and data models documented so that Milestone 2 can be built on them. | MUST HAVE | none | Bishalakshi | 3- Completed
Sprint 1 | Sprint 1 | US-08 | As a developer, I want REST endpoints to validate code, upload files and search the knowledge base so that the UI and agents can reuse them. | SHOULD HAVE | US-01, US-04 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-09 | As a developer, I want code-quality issues such as long functions, too many parameters, high complexity, deep nesting and duplicated code to be detected in Python and Java so that I can improve code maintainability. | MUST HAVE | US-04 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-10 | As a developer, I want security vulnerabilities such as hard-coded credentials, weak hashing, unsafe shell execution and insecure deserialization to be detected so that I can fix unsafe code before release. | MUST HAVE | US-01 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-11 | As a developer, I want SQL injection to be detected in Python and Java code, including user input that flows into a query, so that unsafe database queries are identified. | MUST HAVE | US-10 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-12 | As a developer, I want the code-quality and security agents to analyze the submitted code together, in parallel, so that I receive one consolidated list of findings. | MUST HAVE | US-09, US-10 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-13 | As a developer, I want every finding to show severity, rule id, line number, evidence, OWASP / CWE reference and a suggested remediation so that I can understand and fix it. | MUST HAVE | US-12 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-14 | As a developer, I want the analysis to handle an agent failure gracefully so that one failed agent does not stop the whole review. | SHOULD HAVE | US-12 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-15 | As a developer, I want a risk score, a code-quality score and a technical-debt estimate for each submission so that I can judge the overall state of my code. | SHOULD HAVE | US-13 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-16 | As a tester, I want the detection accuracy to be validated on vulnerable and clean Python and Java samples with known issues so that I can assess precision, recall and false positives. | MUST HAVE | US-09, US-10, US-12 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-17 | As a project stakeholder, I want the README, design notes and Milestone 2 documents updated so that the implementation, supported checks and limitations are documented. | SHOULD HAVE | US-12, US-16 | Bishalakshi | 3- Completed
Sprint 2 | Sprint 2 | US-18 | As a project stakeholder, I want a Milestone 2 presentation with demo screenshots so that the agents and their accuracy can be evaluated. | MUST HAVE | US-16 | Bishalakshi | 2- In Progress
Sprint 3 | Sprint 3 | US-19 | As a developer, I want a Remediation Agent that proposes corrected code for every finding so that I can apply fixes quickly. | MUST HAVE | US-13 |  | 1- Not Started
Sprint 3 | Sprint 3 | US-20 | As a developer, I want to keep a history of reviews and export a report with severity breakdown so that I can track improvement over time. | SHOULD HAVE | US-15 |  | 1- Not Started
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 37 | 0 | 0 | 0 | 14.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Study OWASP Top 10:2025, secure coding guidelines and code smells; prepare notes | 2026-10-15 | 2026-10-15 | Bishalakshi | Others | 3- Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Study RAG architecture: chunking, embeddings, vector store, retrieval | 2026-10-15 | 2026-10-15 | Bishalakshi | Others | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Download OWASP Top 10:2025 and OWASP Cheat Sheets from the official GitHub repositories; convert to markdown with a metadata header (source, licence, category, language) | 2026-10-16 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-04 | Add Python and Java code-quality sources (PEP 8/257/20, Google style guides) and original security-pitfall and code-smell guides; write sources.md | 2026-10-16 | 2026-10-16 | Bishalakshi | Others | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-05 | Build the ingestion pipeline: loader, heading-aware chunking, TF-IDF / sentence-transformer embeddings, persistent vector store | 2026-10-15 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-06 | Build FastAPI prototype with /validate, /upload and /kb/search endpoints | 2026-10-15 | 2026-10-15 | Bishalakshi | Coding | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-07 | Build the Streamlit code submission page with file upload and paste area; upload checks (500 KB limit, UTF-8, binary and empty files) | 2026-10-16 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-08 | Language detector using file extension, keyword patterns and parser check; reject C/C++, JavaScript and C# | 2026-10-16 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-09 | Python syntax validator using compile() and Java syntax validator using javalang | 2026-10-15 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 2.5 | 0 | 0 | 0 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-10 | Show the code with line numbers and highlight the error line; fix the missing-semicolon line number for Java | 2026-10-16 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-11 | Disable the Submit button until the code has no syntax errors | 2026-10-16 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-12 | Pattern-to-guideline retrieval: detect risky Python/Java patterns per line and fetch matching guidance from the knowledge base | 2026-10-16 | 2026-10-16 | Bishalakshi | Coding | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-13 | Design: system architecture, agent responsibilities, orchestration flow and data models diagrams | 2026-10-15 | 2026-10-15 | Bishalakshi | Design | 3- Completed | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-14 | Write 22 pytest unit tests (parsers, RAG, dashboard) and run the API test cases | 2026-10-15 | 2026-10-16 | Bishalakshi | Unit Test | 3- Completed | 3 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-15 | Dashboard testing with sample correct, wrong and vulnerable Python/Java files | 2026-10-16 | 2026-10-16 | Bishalakshi | System Test | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-16 | Prepare the Milestone 1 presentation with demo screenshots | 2026-10-16 | 2026-10-16 | Bishalakshi | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Running pytest from the Downloads folder failed with FileNotFoundError: the kb_docs folder was missing, because it was not part of the downloaded files. | Resolved file paths relative to the module, added a setup script (setup_kb_docs.py) and a clear error message; pytest then showed 11 passed.
Sprint 1 | Day 5 | The MITRE CWE catalogue and SEI CERT wiki pages could not be downloaded directly. | Used the official GitHub repositories (OWASP Top10, OWASP Cheat Sheet Series, PEP, Google style guides) instead; CWE and CERT are noted in sources.md as future additions.
Sprint 1 | Day 5 | The downloaded sources were in different formats: markdown with image tags, reStructuredText (PEP 8) and HTML (Java style guide). | Converted rst and HTML to markdown with pandoc and wrote a cleaning step that removes image tags and attribute markup; every file now has a metadata header.
Sprint 1 | Day 5 | TF-IDF search returned an unrelated chunk first for a loose query such as 'hardcoded passwords in code'. | Mapped each risky code pattern to a focused query and added an optional sentence-transformers backend for semantic search.
Sprint 1 | Day 5 | The Python validator based on ast.parse accepted a 'return' outside a function, and the Java parser reported a missing semicolon on the next line. | Switched to compile() for Python and added a check that points to the line that is really missing the semicolon.
Sprint 2 | Day 2 | javalang does not store positions for catch blocks, operators or the end of a method, so line numbers and complexity could not be read from its tree alone. | Used the javalang syntax tree for classes, methods and imports and the token stream (which has line numbers) for complexity, nesting, catch blocks and comparisons.
Sprint 2 | Day 3 | Security findings in Java pointed to the class line instead of the vulnerable line because a whole class body was joined into one statement. | Statements are now joined only while round or square brackets are open; line numbers verified on the sample files.
Sprint 2 | Day 3 | Parameterised queries that receive user input were reported as SQL injection. | The rule now checks only the query argument, not the bound parameters.
Sprint 2 | Day 4 | Words inside string literals (for example 'id' in an SQL text) were treated as tainted variables. | Strings are blanked before variable names are matched; f-string parts are kept.
Sprint 2 | Day 4 | os.system(cmd) and Runtime.exec(cmd) with a variable command were not reported on test_files/vulnerable.py and Vulnerable.java. | A non-literal command is now reported as a potential command injection (medium confidence).
Sprint 2 | Day 4 | First run on the held-out samples gave 85% precision for the Code Analysis Agent. | Reviewed each false positive one by one; fixed the real bugs and documented the remaining limitation in the validation report.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-10-12 | 2026-10-16 | Bishalakshi | Running tests from the project root and checking file paths early; updating the Agile sheets every day; testing with sample correct, wrong and vulnerable files. | Starting the study and build late in the sprint; downloading material without noting its source, version and licence. | Using official sources (OWASP, PEP, Google style guides); writing unit tests together with each module; keeping the design diagrams up to date. | Added sources.md with source and licence for every document, 22 pytest tests, and a setup script. Plan tasks from Day 1 of the next sprint.
2 | 2 | 2026-10-26 | 2026-10-30 | Bishalakshi | Building a held-out labelled test set before tuning the detection rules. | Tuning the rules only against our own sample files; leaving the report numbers to the last day. | Writing unit tests with each module; keeping the agents independent of the UI. | Added samples_holdout/, an accuracy gate in the pytest suite and the first-run numbers in docs/validation_report.md.

## Sprint 2 Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 44.5 | 6.5 | 8.5 | 11 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-12 | T-17 | Design the unified finding model, severity pyramid, scoring and agent interface | 2026-10-26 | 2026-10-26 | Bishalakshi | Design | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-18 | Python Code Analysis Agent with ast: cyclomatic complexity, function length, parameters, nesting | 2026-10-26 | 2026-10-27 | Bishalakshi | Coding | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-19 | Python smells: bare / empty / broad except, mutable defaults, unused imports, duplicate code, magic numbers | 2026-10-26 | 2026-10-27 | Bishalakshi | Coding | 3- Completed | 2.5 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-20 | Java Code Analysis with javalang: complexity, nesting, god class, catch blocks, string equality, imports | 2026-10-27 | 2026-10-28 | Bishalakshi | Coding | 3- Completed | 3.5 | 0 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-21 | Taint tracking and source / sink catalog for Python and Java | 2026-10-27 | 2026-10-28 | Bishalakshi | Coding | 3- Completed | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-22 | Injection rules: SQL, command, code, XSS, template injection, path traversal, SSRF | 2026-10-28 | 2026-10-29 | Bishalakshi | Coding | 3- Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-23 | Secrets, weak crypto, deserialization, access control and configuration rules with OWASP / CWE mapping | 2026-10-28 | 2026-10-29 | Bishalakshi | Coding | 3- Completed | 3.5 | 0 | 0 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-24 | Orchestrator: run both agents in parallel, merge and de-duplicate findings | 2026-10-28 | 2026-10-29 | Bishalakshi | Coding | 3- Completed | 2.5 | 0 | 0 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-25 | Scoring engine: severity pyramid, risk score, code-quality score, technical debt | 2026-10-28 | 2026-10-29 | Bishalakshi | Coding | 3- Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-26 | Integrate the agents in the Streamlit dashboard: agent status, finding cards, filters, flagged lines, JSON export | 2026-10-28 | 2026-10-29 | Bishalakshi | Integration | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-27 | Labelled sample codebases (vulnerable, smelly, clean) in Python and Java | 2026-10-26 | 2026-10-27 | Bishalakshi | Others | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-28 | Accuracy script (precision / recall) and held-out sample set | 2026-10-28 | 2026-10-29 | Bishalakshi | Coding | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-29 | Write 25 pytest tests for agents, orchestrator, failure isolation, accuracy gate and dashboard | 2026-10-28 | 2026-10-29 | Bishalakshi | Unit Test | 3- Completed | 3 | 0 | 0 | 0.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-30 | Dashboard testing with vulnerable, smelly and clean Python and Java files | 2026-10-29 | 2026-10-29 | Bishalakshi | System Test | 3- Completed | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-31 | Update README, write design notes, validation report and step-by-step guide | 2026-10-29 | 2026-10-29 | Bishalakshi | Others | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-32 | Prepare the Milestone 2 presentation with demo screenshots | 2026-10-29 | 2026-10-30 | Bishalakshi | Others | 2- In Progress | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work