## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Bishalakshi | 2026-10-15 | Running pytest from the Downloads folder failed with FileNotFoundError: the kb_docs folder was not found. | Sprint 1 | Bishalakshi | Logical | Resolved paths relative to the module, added setup_kb_docs.py and a clear error message. | 2026-10-15 | Closed | pytest then showed 11 passed (screenshot saved).
2 | Bishalakshi | 2026-10-16 | Downloaded OWASP Top 10 markdown contained image tags and attribute markup, which would add noise to the chunks. | Sprint 1 | Bishalakshi | Standards | Added a cleaning step in the knowledge base build script that removes images, attribute markup and HTML tags. | 2026-10-16 | Closed | Cleaned files re-generated for all 11 Top 10 documents.
3 | Bishalakshi | 2026-10-16 | The Python validator built on ast.parse() accepted code with 'return' outside a function, so invalid code passed. | Sprint 1 | Bishalakshi | Logical | Replaced ast.parse() with compile(), which catches these errors and still never executes the code. | 2026-10-16 | Closed | test_python_return_outside_function_caught passes.
4 | Bishalakshi | 2026-10-16 | A missing semicolon in Java was reported on the next line (line 4 instead of line 3). | Sprint 1 | Bishalakshi | Logical | Added a check that points to the previous code line when it does not end with a valid terminator. | 2026-10-16 | Closed | test_java_missing_semicolon_points_to_right_line passes.
5 | Bishalakshi | 2026-10-16 | TF-IDF search returned an unrelated chunk first for the loose query 'hardcoded passwords in code'. | Sprint 1 | Bishalakshi | Others | Dashboard uses focused queries for each code pattern; a sentence-transformers backend can be selected in the sidebar. | 2026-10-16 | Open | Known limitation of keyword search for free-text questions; re-test with the semantic backend in Milestone 2.
6 | Bishalakshi | 2026-10-16 | Chunk overlap started in the middle of a word (for example 'abase queries'). | Sprint 1 | Bishalakshi | Maintainability | Overlap now starts at a word boundary. | 2026-10-16 | Closed | Index rebuilt and all 22 tests pass.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others