## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Bishalakshi | 2026-10-15 | Running pytest from the Downloads folder failed with FileNotFoundError: the kb_docs folder was not found. | Sprint 1 | Bishalakshi | Logical | Resolved paths relative to the module, added setup_kb_docs.py and a clear error message. | 2026-10-15 | Closed | pytest then showed 11 passed (screenshot saved).
2 | Bishalakshi | 2026-10-16 | Downloaded OWASP Top 10 markdown contained image tags and attribute markup, which would add noise to the chunks. | Sprint 1 | Bishalakshi | Standards | Added a cleaning step in the knowledge base build script that removes images, attribute markup and HTML tags. | 2026-10-16 | Closed | Cleaned files re-generated for all 11 Top 10 documents.
3 | Bishalakshi | 2026-10-16 | The Python validator built on ast.parse() accepted code with 'return' outside a function, so invalid code passed. | Sprint 1 | Bishalakshi | Logical | Replaced ast.parse() with compile(), which catches these errors and still never executes the code. | 2026-10-16 | Closed | test_python_return_outside_function_caught passes.
4 | Bishalakshi | 2026-10-16 | A missing semicolon in Java was reported on the next line (line 4 instead of line 3). | Sprint 1 | Bishalakshi | Logical | Added a check that points to the previous code line when it does not end with a valid terminator. | 2026-10-16 | Closed | test_java_missing_semicolon_points_to_right_line passes.
5 | Bishalakshi | 2026-10-16 | TF-IDF search returned an unrelated chunk first for the loose query 'hardcoded passwords in code'. | Sprint 1 | Bishalakshi | Others | Dashboard uses focused queries for each code pattern; a sentence-transformers backend can be selected in the sidebar. | 2026-10-16 | Open | Known limitation of keyword search for free-text questions; re-test with the semantic backend in Milestone 2.
6 | Bishalakshi | 2026-10-16 | Chunk overlap started in the middle of a word (for example 'abase queries'). | Sprint 1 | Bishalakshi | Maintainability | Overlap now starts at a word boundary. | 2026-10-16 | Closed | Index rebuilt and all 22 tests pass.
7 | Bishalakshi | 2026-10-28 | Security findings in Java pointed to the class line instead of the vulnerable line (a whole class body was joined into one statement). | Sprint 2 | Bishalakshi | Logical | Statements are joined only while round or square brackets are open. | 2026-10-28 | Closed | Found by the first accuracy run (19 of 37 Security issues missed).
8 | Bishalakshi | 2026-10-28 | Parameterised queries that receive user input (execute(sql, (n,))) were reported as SQL injection. | Sprint 2 | Bishalakshi | Logical | Only the query argument is checked for user data, not the bound parameters. | 2026-10-28 | Closed | test_parameterised_query_is_not_flagged passes.
9 | Bishalakshi | 2026-10-28 | System.out.println(...) matched the XSS response-writer pattern. | Sprint 2 | Bishalakshi | Logical | The writer pattern no longer matches when 'out' follows a dot. | 2026-10-28 | Closed
10 | Bishalakshi | 2026-10-29 | Words inside string literals (for example 'id' in an SQL text) were treated as tainted variables. | Sprint 2 | Bishalakshi | Logical | Strings are blanked before variable names are matched; f-string parts are kept. | 2026-10-29 | Closed | Found while reviewing false positives.
11 | Bishalakshi | 2026-10-29 | A @PreAuthorize annotation placed above the route annotation was ignored, so a protected endpoint was reported. | Sprint 2 | Bishalakshi | Logical | The access-control check now also reads the annotations stacked above the route. | 2026-10-29 | Closed | Found by the first run on the held-out samples.
12 | Bishalakshi | 2026-10-29 | Code-looking text inside a string literal triggered the SQL injection rule. | Sprint 2 | Bishalakshi | Logical | Sink patterns that start inside a string literal are ignored. | 2026-10-29 | Closed | test_comments_and_string_words_do_not_trigger passes.
13 | Bishalakshi | 2026-10-29 | A value cleaned with shlex.quote() and then concatenated into a command was still reported as command injection. | Sprint 2 | Bishalakshi | Logical | Built strings that contain a sanitiser call and no user data are not reported. | 2026-10-29 | Closed | test_sanitised_input_is_not_flagged passes.
14 | Bishalakshi | 2026-10-29 | A hard-coded secret written as config["SECRET_KEY"] = "..." was not detected. | Sprint 2 | Bishalakshi | Standards | The secret pattern now allows a closing bracket before '='. | 2026-10-29 | Closed
15 | Bishalakshi | 2026-10-29 | os.system(cmd) and Runtime.exec(cmd) with a variable command were not reported on test_files/vulnerable.py and Vulnerable.java. | Sprint 2 | Bishalakshi | Logical | A non-literal command is now reported as a potential command injection (medium confidence). | 2026-10-29 | Closed | Literal commands such as os.system("ls -l") are still not reported.
16 | Bishalakshi | 2026-10-29 | An unreachable statement directly after a method's opening brace was missed in Java. | Sprint 2 | Bishalakshi | Logical | The token scan now also checks the first statement of a method body. | 2026-10-29 | Closed | Found by the accuracy run after the javalang port.
17 | Bishalakshi | 2026-10-29 | The radix argument in Long.toString(x, 36) is reported as a magic number. | Sprint 2 | Bishalakshi | Maintainability |  |  | Open | Known limitation, documented in docs/validation_report.md; one false positive on the held-out set.
18 | Bishalakshi | 2026-10-29 | Valid Java 14+ syntax (records, switch expressions, text blocks) is rejected as a syntax error because javalang supports only older Java. | Sprint 2 | Bishalakshi | Others |  |  | Open | Pre-existing limitation of the Milestone 1 validator, so the agents never run on such code. Option: call javac when a JDK is installed.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others